## Gantt Chart
[7 empty] | Period Highlight: |  |  |  |  | 7 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  | Actual (beyond plan) | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | 2017-07-01 | 2017-07-08 | 2017-07-15 | 2017-07-22 | 2017-07-29 | 2017-08-05 | 2017-08-12 | 2017-08-19 | 2017-08-26 | 2017-09-02 | 2017-09-09 | 2017-09-16 | 2017-09-23 | 2017-09-30 | 2017-10-07 | 2017-10-14 | 2017-10-21 | 2017-10-28 | Comments
| START | DURATION | START | DURATION | COMPLETE
ACTIVITY | [5 empty] | RISK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Scoping of the project | 1 | 1 | 1 | 1 | 100%
1. Imbalanced Parts Optimization | 1 | 1 | 1 | 1 | 100%
2. DPP Production Planning | 1 | 1
1. Imbalanced Parts Optimization
A. Initial model with basic understanding | 2 | 2 | 2 | 3 | 100%
B. Mixed Integer Linear Programming Model | 5 | 7 | 5 |  | 20%
a. Comprehensive understanding of cutting pattern | 5 | 1 | 5 | 1 | 100%
b. Defining various constraints | 5 | 2 | 5 | 2
c. Mathematical Formulation | 6 | 3 | 6
e. Data collection (parallel process) | 5 | 7 | 5
d. Apply model to actual production data | 9 | 3
f. Excel Template for user | 6 | 6
2. DPP Production Planning
DPP Production Planning Optimization

## RASCI (hidden)
Project RASCI: SKU Rationalization |  |  |  | R | A | S | C | I
Duties | Tasks | Frequency / Timeline | Roles F OutputsD | Plant Rep. (Sik & Danny) | Knex Consultant | Knex PM | Mr. Derrick | Sales | Mr. Victor | Dr. Mahender | MD
Data Sheet Compilation | SKU Differenciation (Lumut Vs. PG) | 2016-09-06 |  | R | A | C | C | I | I | I | I
| Sales & Margin Information by SKU | 2016-09-06 |  | C | R | A | C | C | I | I | I
| Mother & Base Flour Information | 2016-09-06 |  | R | A | C | C | I | I | I | I
| Trend Study | 2016-09-06 |  | C | R | A | C | C | I | I | I
| MTO/MTS | 2016-09-06 |  | R | A | C | C | I | I | I | I
| Customer & Channel data | 2016-09-06 |  | C | R | A | C | C | I | I | I
| Costing Information (Mfg, Pkg., Trans) | 2016-09-06 |  | C | R | A | C | C | I | I | I
| Inventory Turns | 2016-09-06 |  | C | R | A | C | C | I | I | I
| Flour Protein & Gluten Level | 2016-09-06 |  | R | A | C | C | I | I | I | I
| Marketing Inputs | 2016-09-09 |  | C | C | C | C | R | A | I | I
Complexity Ranking | Supply Chain Complexity | 2016-09-13 |  | C | R | A | C | C | I | I | I
Presentation | Final Presentation | 2016-09-14 |  | C | R | A | C | C | C | I | I
| Accommodate Changes | 2016-09-20 |  | C | R | A | C | C | C | I | I
Results | Publish Results | 2016-09-29 |  | C | C | C | A | C | R | I | I
Note on E3: Responsible: Those who do the work to achieve the task. There is typically one role with a participation type of Responsible, although others can be delegated to assist in the work required
Note on F3: Accountable (also Approver or final Approving authority) Those who are ultimately accountable for the correct and thorough completion of the deliverable or task, and the one to whom Responsible is accountable. In other words, an Accountable must sign off (Approve) on work that Responsible provides. There must be only one Accountable specified for each task or deliverable.
Note on G3: Support Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
Note on H3: Consulted Those whose opinions are sought; and with whom there is two-way communication.
Note on I3: Informed Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication